## 2012-13
Date | Request | Who is Responsible | Date Completed | Status / Notes
Active
2016-04-20 | Provide information on change in phasing of SOM modernization. | Karl |  | Contract for SOM Project 1B was awarded at April 9, 2013, board meeting. No supporting documentation found.
2016-03-23 | How many dollars from Prop O proceeds have been expended on legal fees to date? | Karl |  | Exhibit 1: Sample Legal Fees Breakdown Document
2016-03-20 | Provide a cost/benefit analysis comparing synthetic and natural turf. | Karl |  | Clarification: HTH and BVH projects have been approved by board as synthetic track and turf projects.
2015-11-10 | Prop O soft costs by month. | Karl |  | Pending. This information is not included in 5-20-16 exhibit 2 as previously stated. Staff to generate report.
2015-08-19 | Additional detail on T&I Costs, What are industry standards? | Karl |  | 4% - 6% is typical on our projects. Staff will research industry standards.
2015-07-22 | Data on Expenditures by School of Specific Projects/Functions. | Karl |  | SDCOE representative to give report under agenda item 7.d. regarding new software that will generate requested reports.
Complete
2016-04-20 | Provide copy of Steven Hawking Charter MOU | Karl |  | Provided as Exhibit 1 at May 20, 2016 meeting.
2016-03-23 | What is the debt limit capacity for the district? | Karl |  | Mr. Marinovich stated that he received this information and will share with committee.
2016-03-20 | Provide a cost/benefit analysis comparing synthetic and natural turf. | Karl |  | Exhibit 3 at May 20, 2016 meeting.
2015-10-21 | What are the delay costs (a/e, ior) for NCM P2? | Karl | 2016-04-20 | This item was removed from the data request log per discussion with committee on 4/20/16
2015-10-21 | What are the delay costs (a/e, ior) for MVH P2 600 Building? | Karl | 2016-04-20 | This item was removed from the data request log per discussion with committee on 4/20/16
2015-10-21 | Graph or expenditure table comparing Planning and Ops expenditures to total Prop O expenditures by Month. | Karl | 2016-04-20 | This request is covered under third item on active list above.
2015-08-19 | PPA Relevant internal correspondence on the evalulation and selection process. | Karl | 2016-04-20 | Attachment 2. RFQ package was provided at 3/23/16 meeting. This item may be brought back for discussion pending review by Mr. O'Neill.
2015-11-10 | Warranty Logs - provide status report | Karl | 2016-03-23
2015-11-10 | iPads - has Prop O been repaid. | Karl/Fiscal | 2016-03-23 | $1.8M in Prop O interest earnings were expended. No bond proceeds were used.
2015-11-10 | List of Contractors (Kevin) | Karl | 2016-03-23 | Exhibit 1
2015-10-21 | Add total classroom count to Number of Classrooms Modernized with Prop BB & O. | Karl | 2016-03-23 | Exhibit 2
2015-09-25 | Cost to air-condition all remaining classrooms. | Karl | 2016-03-23 | Construction costs estimated at ~$7.2M for classrooms only.
2015-09-09 | Electrical rates per kwh for solar, commodity puchase and SDG&E | Karl | 2016-02-17 | Complete. Submitted at Feb 17, 2016 CBOC Meeting.
2015-08-19 | PPA RFP Responses, Evaluation Committee and Criteria for selection | Karl | 2016-03-23 | Exhibit 3 (pg. 19 has evaluation criteria)
2015-08-19 | Furniture Fixtures and Equipment Expenditures | Karl | 2016-03-23 | Complete. Submitted at March 23, 2016, CBOC Meeting.
2016-02-17 | LRFMP - Final payment to Jacobs | Moisés |  | Complete
2015-08-19 | Assessed Value and Debt Capacity Projections | Finance | 2015-10-21 | Item is on the 10/21 CBOC meeting agenda
2015-08-19 | PPA 1 pre-installation cost benefit analysis | Paul | 2015-10-21 | This document is posted on the Prop O Website. http://buildingpropo.sweetwaterschools.org/files/2012/08/SUHSD-Solar-Final-Recommendations-3.10.11.pdf
2015-08-19 | PPA 2 pre-installation cost benefit analysis | Paul | 2015-10-21 | This document is posted on the Prop O Website. http://buildingpropo.sweetwaterschools.org/files/2012/08/Solar-Project-Analysis-1B-and-2.pdf
2015-08-19 | PPA Cost to date | Paul | 2015-10-21 | $412,042 through 9/30/15 (reported on the CFFP and CBOC reports every month).
2015-08-19 | Graph or expenditure table comparing Planning and Ops expenditures to total Prop O expenditures | Paul | 2015-10-21 | Report is on the 10/21 CBOC meeting agenda
2015-09-25 | Number of classrooms modernized by Prop BB & O | Paul | 2015-10-21 | Report is on the 10/21 CBOC meeting agenda
2015-08-19 | Additional detail on Legal Costs | Paul / Jennie | 2015-10-21 | Detail for 13/14 and 14/15 is on the 10/21 CBOC meeting agenda
2015-07-22 | Warranty Logs | Paul / Gary | na | Reviewed at a number of meetings. Comprehensive log not kept by Maintenance. Warranty list available per project
2015-07-22 | Copy of SOM Site Meeting #2 12/17/07 sign-in sheet | Paul | na | To date, staff has been unable to locate this item.
2015-07-22 | Breakdown of Inspection Costs | Paul | 2015-08-19 | Complete. Submitted at Aug 19, 2015 CBOC Meeting
2015-07-22 | Charter School Costs with Proposition O (if any) | Paul | 2015-08-19 | Complete. Submitted at Aug 19, 2015 CBOC Meeting
2015-07-22 | Legal Costs funded with Proposition O | Paul / Jennie / Deanne | 2015-08-19 | Complete. Submitted at Aug 19, 2015 CBOC Meeting
2015-07-22 | CEQA Review for Projects | Paul | 2015-08-19 | Presented orally at the August 19, 2015 CBOC Meeting
2015-07-22 | Org Chart and Staff for Maintenance | Gary | 2015-07-22 | Complete. Submitted at Jul 22, 2015 CBOC Meeting